## Instructions
Project Register Template v3
Use with the Project Status & Resource Engagement Plan Dashboard.
HOW TO USE
1. Add or edit master data first: sheets Resources, Projects, Holidays_Leave. Lists holds roles, test statuses and priorities.
2. Enter work on the 'Project Register' sheet, one task per row, starting at row 2. Keep the header row unchanged.
3. Open the 'Data Check' sheet. Every row should say OK before you import. It also shows the allocation % each person gets on that task.
4. Import 'Project Register' into the dashboard (Setup > Import Project Register).
CONVENTIONS (assumptions - change here if your rules differ)
Working week: Sunday to Thursday (Friday and Saturday are weekends). Holidays come from Holidays_Leave.
Effort MD is the TOTAL effort for the task and is split evenly across all assigned resources (Resource 1-3).
Allocation % per person = Effort MD / (working days x number of resources). Leave 'Allocation / Resource' as Auto; the dashboard calculates it.
Only Test Statuses marked 'Yes' in Lists > 'Counts toward load' are included in workload. Change the flags in Lists as needed.
Resource names must match the Resources sheet exactly (dropdown). Role is per assignment and defaults to the person's usual role.
Dropdown ranges cover rows 2-500 of the register. Role 'Technical Lead' replaces the old 'Technical Lead, SQA' because the comma broke Excel dropdowns and CSV import.
COLOUR LEGEND
Blue text = value you type (inputs)
Black text = formula, do not overwrite
Yellow fill = configurable setting (Lists flags, Resources capacity)
Orange header = optional columns the dashboard reads when present (Priority, Project Status, Release Date). Delete a column if your dashboard version rejects it.
Project Status "Deployed in Live": on import the row is NOT added to the register; it goes to the dashboard's Deployed in Live section with the Release Date (today if the date is blank).
Rows starting with [DEMO] are examples. Delete them before real use.

## Project Register
Project | JIRA ID | Task Details | PM | Start Date | End Date | Effort MD | Resource 1 | Role 1 | Resource 2 | Role 2 | Resource 3 | Role 3 | Allocation / Resource | Test Status | Priority | Project Status | Release Date
HRMS | DEMO-HRMS-001 | [DEMO] Employee Profile Enhancement | Demo PM | 2026-10-04 | 2026-10-08 | 5 | Demo Resource A | SQA Engineer |  |  |  |  | Auto | Testing In Progress | High | In Testing
E-Recruitment | DEMO-REC-001 | [DEMO] Candidate Search Improvement (overlaps A) | Demo PM | 2026-10-04 | 2026-10-08 | 3 | Demo Resource A | SQA Engineer | Demo Resource B | Sr. SQA Engineer |  |  | Auto | Test Case Review | Medium
BHP | DEMO-BHP-001 | [DEMO] Dashboard Regression Testing | Demo PM | 2026-10-11 | 2026-10-15 | 4 | Demo Resource C | Lead SQA Engineer |  |  |  |  | Auto | Regression Testing | High
FM Dashboard | DEMO-FM-001 | [DEMO] Urgent Hotfix Verification (overlaps C) | Demo PM | 2026-10-11 | 2026-10-13 | 3 | Demo Resource C | Lead SQA Engineer |  |  |  |  | Auto | Ready for Testing | Critical
CMN | DEMO-CMN-001 | [DEMO] API Integration Validation | Demo PM | 2026-10-11 | 2026-10-15 | 4 | Demo Resource B | Sr. SQA Engineer | Demo Resource D | Jr. SQA Engineer |  |  | Auto | Test Case Writing | Medium
ED Dashboard | DEMO-ED-001 | [DEMO] Report Filter Checks (under-used week) | Demo PM | 2026-10-18 | 2026-10-22 | 2 | Demo Resource B | Sr. SQA Engineer |  |  |  |  | Auto | Not Started | Low
BSL | DEMO-BSL-001 | [DEMO] Loan Module Smoke Test | Demo PM | 2026-10-18 | 2026-10-22 | 5 | Demo Resource D | Jr. SQA Engineer |  |  |  |  | Auto | Ready for Testing | Medium
BRAC International | DEMO-BRAC-001 | [DEMO] Three-person Release Testing | Demo PM | 2026-10-25 | 2026-10-29 | 6 | Demo Resource A | SQA Engineer | Demo Resource B | Sr. SQA Engineer | Demo Resource C | Lead SQA Engineer | Auto | Not Started | High
BBSO | DEMO-BBSO-001 | [DEMO] Already live - goes to Deployed in Live | Demo PM | 2026-09-20 | 2026-09-24 | 5 | Demo Resource A | SQA Engineer |  |  |  |  | Auto | Completed | Low | Deployed in Live | 2026-09-25
Note on G1: Total man-days for the task, split evenly across all assigned resources.
Note on N1: Leave as 'Auto'. The dashboard calculates allocation per resource.
Note on P1: Optional. Delete this column if your dashboard version rejects extra columns.
Note on Q1: Optional. Pick "Deployed in Live" to file the row under Deployed in Live on import. Other values are free text managed in the dashboard.
Note on R1: Only used when Project Status is Deployed in Live. Blank = import date.

## Data Check
Register Row | JIRA ID | Working Days | Resources | Allocation / Resource | Issues | Result
2 | DEMO-HRMS-001 | 5 | 1 | 100% |  | OK
3 | DEMO-REC-001 | 5 | 2 | 30% |  | OK
4 | DEMO-BHP-001 | 5 | 1 | 80% |  | OK
5 | DEMO-FM-001 | 3 | 1 | 100% |  | OK
6 | DEMO-CMN-001 | 5 | 2 | 40% |  | OK
7 | DEMO-ED-001 | 5 | 1 | 40% |  | OK
8 | DEMO-BSL-001 | 5 | 1 | 100% |  | OK
9 | DEMO-BRAC-001 | 5 | 3 | 40% |  | OK
10 | DEMO-BBSO-001 | 5 | 1 | 100% |  | OK

## Resources
Resource Name | Default Role | Capacity % | Active | Notes
Demo Resource A | SQA Engineer | 100% | Yes | Capacity % is the share of the working week available for project work (100% = full time; use e.g. 80% if 20% goes to support or meetings).
Demo Resource B | Sr. SQA Engineer | 100% | Yes | Add up to 50 resources (rows 2-51). Names here feed the Resource 1-3 dropdowns.
Demo Resource C | Lead SQA Engineer | 100% | Yes
Demo Resource D | Jr. SQA Engineer | 100% | Yes

## Projects
Project | Active | Add new projects below the last one (rows up to 100). The Project dropdown on the register reads this list.
HRMS | Yes
E-Recruitment | Yes
FM Dashboard | Yes
ED Dashboard | Yes
BHP | Yes
BSL | Yes
BRAC International | Yes
BBSO | Yes
CMN | Yes

## Holidays_Leave
Company Holidays |  | Planned Leave |  |  |  | Note
Date | Holiday | Resource | Leave From | Leave To | Type | Holidays reduce working days in 'Data Check'. Leave rows are for the dashboard's capacity forecast; confirm your dashboard version reads this sheet before relying on it.
2026-12-16 | [DEMO] Victory Day | Demo Resource B | 2026-11-08 | 2026-11-12 | Annual Leave

## Lists
Roles | Test Status | Counts toward load? | Note | Priority | Project Status | Only "Deployed in Live" has special meaning in the dashboard. The other values are examples; edit freely.
Technical Lead | Not Started | Yes | Planned work, counts as upcoming load | Critical | Unspecified
Lead SQA Engineer | Test Case Writing | Yes |  | High | In Planning
Sr. SQA Engineer | Test Case Review | Yes |  | Medium | In Development
SQA Engineer | TCW Done | Yes | Writing done, execution still ahead | Low | In Testing
Jr. SQA Engineer | Ready for Testing | Yes |  |  | UAT
Intern | Testing In Progress | Yes |  |  | Ready to GoLive
| TCE In Progress | Yes |  |  | Deployed in Live
| TCE Halt / Blocked | Yes | Resource is still reserved
| TCE Done | No | Execution finished
| Retesting | Yes
| Regression Testing | Yes
| UAT In Progress | Yes
| UAT Support | Yes
| UAT Halt / Blocked | Yes | Resource is still reserved
| UAT Done | No
| Passed | No
| Failed | Yes | Assumption: failed work will be retested. Set to No if closed.
| On Hold | No | Assumption: no capacity reserved while on hold.
| Completed | No